Community Change Log

Vision of Health Priority Area:  Breaking the Cycle of Substance Abuse

# DOH Staff Coach(es):  Phil Teakell

Core Team Members: Noreen Hendrickson (Chair), Dee Reed, Gail Cook, Susan Lease, Tim Gutierrez, Lt. Nathan Wallace, Mary Ann Dominguez, Alan Angel, George Arguello, & Edna Cleary

Vision of Health Indicator: Reducing the illicit drug use prevalence among adolescents.

|  |  |  | # Activity Description | # Systems Approach Tools |
| --- | --- | --- | --- | --- |
| # Entry # | Date | # System Approach Element: Aim Work Improvement | - What virtual system members were participating? - Was this the first time this activity occurred? - Describe the aim, work or improvement activity. - What are the next steps? | - What systems approach tool was used to facilitate this activity? - What were the lessons learned / competencies gained or improved? |
| 1 | 9-30-02 | Aim | - Core committee - Yes - We had our first two scheduled meetings to work on our aim and determine the appropriate membership for the core team. - Inviting identified potential members. | - All on the wall to begin identification of the aim. - It is difficult to identify potential members who can meet during the currently scheduled meeting time. |
| 2 | 9-30-02 | Work | - Core Committee - Yes - Worked on a Charter between the MCCH Council and the Substance Abuse Core Committee - Develop a DRAFT Charter minus Aim, which will be decided later. | - Charter DRAFT Provided by coaches - Important of a Charter in setting guidelines for the Council and the Committee. |
| 3 | 12-30-02 | Aim | - Core committee - No - In determining the Aim, the committee chose to repeat the “All on the Wall” activity. The committee felt that they needed to repeat this activity in order to be more thorough. - Give serious personal and research consideration to this Aim and review the work at the next meeting. | - Determine the Aim using “All on the Wall” activity. - Importance of a taking time in determining the Aim in order to include everyone and all currently available information. |
| 4 | 12-30-02 | Work | - Members of the Quay County MCCH Council, including some involved with Core Committee - Yes - 7 individuals attended the “Vision of Health” Conference - Prevent learned concepts from the Conference with the Core Committee and the Council | - Getting as many people involved educated on the issues involved and the current research - 7 attendees was a good-sized group and will provide a good core of individuals to assist in the Substance Abuse process. |
| 5 | 12-30-02 | Aim | - Core Committee - No - Work continues to broaden the membership of the Core Committee to include community folks affected by substances. - Further discussion to identify appropriate individuals and use of budgetary stipends | - Getting and appropriate people involved initially. - This isn’t as easy as it sounds, but perseverance is hopefully the answer! |
| 6 | 12-30-02 | Aim | - Core Committee and Members of the Quay County MCCH Council - No - Identifying New Core Team members that have impact on work toward our aim. - Inviting New Core Team members to the team. | - Getting and appropriate people involved initially. - Thinking outside of our normal groups to see who can help in the process and give us a fuller picture |
| 7 | 03-31-03 | Work | - Core Committee - No - Adding New Core Team members to the team, especially law enforcement and JPPO. - Creating Information Diagraph on adolescent substance abuse. | - Getting and appropriate people involved. - Getting new members is easier when we are confident that our process is leading to needed action. |
| 8 | 03-31-03 | Work | - Core - Yes - Creating Information Diagraph on adolescent substance abuse. - Creating Information Diagraph on key drivers and effects of adolescent substance abuse. | - Informational Diagraph. - We were very surprised to see what the key drivers and effects emerged as compared to our expectations. Everyone sees deep value in these activities. |
| 9 | 03-31-03 | Work | - Core Committee - No - Creating Information Diagraph on key drivers and effects of adolescent substance abuse. - Creating Information Diagraphs on Substance Abuse with high school students. | - Informational Diagraph. - Doing several diagraphs has taught us how to do this in other settings both in and out of the general Council. |
| 10 | 03-31-03 | Work | - Core Committee (expanding) - Yes - Creating flowcharts on law enforcement systems related to substance abuse. - Creating flowcharts on JPPO process. | - Flowcharting. - We are already identifying gaps in services and fractured transitions between agencies. Many commented that they have a far better understanding of the complexities of law enforcement. |
| 11 | 03-31-03 | Work | - Core Committee (expanding) - No - Creating flowcharts on counseling/treatment systems related to substance abuse. - Moving on to next planning stage. | - Flowcharting. - The activity emphasized the need to have the schools more involved in our process. Members are becoming more competent in flowcharting. |
| 12 | 03-31-03 | Work | - Core Committee (expanding) - No - Creating flowcharts on the JPPO systems related to substance abuse. - Moving on to next planning stage. | - Flowcharting. - This re-emphasized the need for greater school representation. |