Community Action Team Change Log

Vision of Health Priority Area:  Promoting Healthy Families

# DOH Staff Coach(es):  Alida Brown, Jay Nemrow

Core Team Members: Yolanda Garcia (chair), Maria Rodriguez (chair), Jessie Robinson, Brenda Bishop, Julie Sursa, Susan Reents, Gail Balzano, Claudia Preciado, Andi Garcia, Mary Ann Dominguez

Vision of Health Indicator: Decreasing the teen birth rate.

|  |  |  | # Activity Description | # Systems Approach Tools |
| --- | --- | --- | --- | --- |
| # Entry # | Date | # System Approach Element: Aim Work Improvement | - What virtual system members were participating? - Was this the first time this activity occurred? - Describe the aim, work or improvement activity. - What are the next steps? | - What systems approach tool was used to facilitate this activity? - What were the lessons learned / competencies gained or improved? |
| 1 | 6-30-03 | Aim | - Whole Committee - Yes - We did Interrelationship Diagraph on causes of teen pregnancy. - Breakout into groups and do diagraphs on key drivers. | - Interrelationship Diagraph. - One needs to put assumptions in their “back pocket” and see what a tool tells us. |
| 2 | 6-30-03 | Aim | - Three groups of committee members - No - Did Interrelationship Diagraphs and reported back results to group. - Decide upon Working Aim and Outcome measure. | - Interrelationship Diagraph - This is going to be a commitment on our parts! |
| 3 | 9-30-03 | Aim | - Whole committee. - No - Presentation on the Teen Pregnancy problem by Public Health Division. - Decide upon Working Aim and Outcome Measure. | - Educate group better on the problem. - Everyone must become educated about the problem and “what works.” |
| 4 | 12-31-03 | Work | - Whole Committee - Yes - Develop Aim and Outcome Measure - Flowcharting | - Aim and Outcome Measure - We need to narrow our attack based on the information we can gather and our own energy. |
| 5 | 12-31-03 | Aim | - Whole committee - Yes - Flowcharted the Families First Program - Many assignments to flowchart processes around teens. | - Flowchart. - It is easy to identify problems while flowcharting and even easier to find fault. We are working to create solutions as partners. |
| 6 | 1-8-04 | Work | - Jessie. - No. - Flowchart the WIC Program - More flowcharting. | - Flowchart. - The perception of a worker compared to a client can be very different. |
| 7 | 1-8-04 | Work | - Whole Committee. - No. - Flowchart WIC from our teen members’ point of view. - Study how teens find out about available programs or services. | - Flowchart. - It is very important to get a “client’s-eye-view” of the process. |
| 8 | 1-21-03 | Work | - Committee and Mrs. Balzano’s classes. - No. - Review and consolidate flowcharts on the decision to have sex by Mrs. Balzano’s students. - Get more information from students. | - Flowchart. - Maybe the decision to have sex can be caught better with something besides a flowchart. |
| 9 | 2-6-04 | Work | - Maria and Mrs. Balzano’s classes. - Yes. - Do Force Field Analyses and Interrelationship Digraphs on teen pregnancy. - Take future steps based on information. | - Force Field Analyses and Interrelationship Digraphs. - There are a few very vocal kids and a whole lot of quiet ones. |
| 10 | 3-18-04 | Work | - Whole Committee. - No. - Create an PDSA to approach the Tucumcari School Superintendent to get a sex ed. curriculum that work. - Research science-based sex ed. Curriculums. | - Find a leverage point and plan a PDSA. - It is hard to settle on one strategy when so much in the system needs work. |