| First Quarter | - Have a health council coordinator. |
| --- | --- |
| By September 1, 2003 | - Start SubAbuse work. |
| By October 1, 2003 | - Begin coaching TeenPreg. |
| By October 15, 2003 | - Quarterly Report |
| By November 1, 2003 | - Develop TeenPreg Charter. |
| Second Quarter |  |
| By January 15, 2003 | - Quarterly Report - Review and update Council organizational documents - In a general or Executive committee meeting with general approval. - Including Definition of Health, by-laws, vision, mission, operational procedures, blah, blah. - List of members that indicates diversity and officer list that indicates change. - MOUs and MOAs between council and agencies/members. - A flyer or brochure that documents: - Definition of health, vision, mission, official recognition, listing of local partners, health status priorities, officers, coordinator, and contact information. |
| Third Quarter | - Administer Community Health Improvement Process tool – Quality Module and use the results to inform council leadership of areas they may want to concentrate development work. |
| By March 30, 2003 | - Review and update Community Health Profile. - Review and update Community Health Improvement Plan. |
| By April 15, 2003 | - Quarterly Report |
| Fourth Quarter |  |
| By July 15, 2003 | - Quarterly Report - Document participation in minimum of 3 quarterly leadership meetings and bring document examples and tools. - Distribute Plan and Profile to coalitions annually. - Attend all four CHITI Coaching Network meetings. |
| Quarterly reports: | - Scope of Work Logs - Community Action Team Change Logs - Minutes, agendas, and attendance lists (from Council Meetings??) - System Planning documents. - Health council meeting minutes where Teams are regular item. |
| CHITI courses | - Reported on provided Matrix form. - Coordinator and co-coordinator must attend one course. - Members (not DOH employees) attend 6 courses. |
| Paranoia Points | - No voting member is part of the fiscal agent organization. |
| Share Fair | - Participation and Exhibit |