Quay County Maternal Child and Community Health Council

1st Quarter FY04 Scope of Work Log

October 15, 2003

- Hire a contractor to provide coordination services for the Comprehensive Community Health Council in the Community Health Improvement Process activities:

  - Develop, maintain, and document the Comprehensive Community Health Council’s community health improvement Process’ Community Building Cycle by:

    - Engage and maintain a Health council Coordinator who is responsible for facilitating health council activities in accordance with the scope of work…  Jason Nemrow is under contract, as of 1 Aug 03, to serve as a co-coordinator.

    - Provide Quarterly Reports which are the Scope of Work Logs and the Community Change Logs… [15 Oct 03; 15 Jan 04; 15 Apr 04; 15 Jul 04]  This is the 15 Oct 03 report.

    - Administer the Community Health Improvement Process Self-Assessment Tool… [15 Apr 04]

    - Provide documentation of attendance at the Community Health Improvement Training Institute (CHITI) courses…  [15 Jul 04]  No Council members have attended CHITI courses as yet.

    - Review and update when appropriate the Comprehensive Community Health Council organizational documents… [15 Jan 04]  This is in process.

    - Ensure no one member in a voting or decision-making role is in both the health council and the fiscal agent organization….  Changes to By-laws are being developed to address this issue.

    - Provide DOH with a current list of members, demonstrating diverse membership… [15 Jan 04]  Not yet reported.

    - Provide DOH with Memoranda of Understanding (MOUs) or… [15 Jan 04] Not yet reported.

    - Provide DOH and disseminate within the community a flyer or brochure which documents… [15 Jan 04] Not yet reported.

    - Provide DOH with documentation of participation and provision or an exhibit in one statewide meeting… [15 Jul 04] Not yet reported.

    - Provide DOH with documentation of participation in a minimum of three quarterly Public Health Division District Area Health Council Leadership meetings… [15 Jul 04] Not yet reported.

  - Update the comprehensive Community Health Council’s community health improvement process’ Assessment & Prioritization Cycle, …, by:

    - Review and update where appropriate the comprehensive Community Health Profile… [30 Mar 04] Not yet reported.

    - Review and update where appropriate the comprehensive Community Health Improvement Plan… [30 Mar 04] Not yet reported.

    - Provide to anyone or any group in the community, …and distribute to other coalitions at lease annually. Current Profile and Plan are on display at http://www.quaymcch.com and FY04 updates will be available at the same web site by the end of the contract period.

  - Provide coordination services, …,  for the Community Health Council’s community health improvement process Community Action Cycle [Youth Illegal Substance Use] … , starting September 1, 2003, by:

    - Attendance at all 4 days …   of the new CHITI Systems Approach Classes/Coaching network meetings is required by all coordination staff… We have elected to sponsor and attend a 2-day DOH Community Systems Change Process training in lieu of the first three days.  This is scheduled for late October 2003.

    - Coordinate the first Community Action Team … starting by September 1, 2003. The first Community Action Team (Substance Abuse Committee) met and was coordinated as specified on August 15, 2003. (See attached meeting minutes.)

    - Assure that the … Community Action Team meets twice a month for a minimum of 4 hours total per month… (See minutes of meetings.)

    - Provide the Health Council and DOH documentation of the work of the Community Action Team… (See attached meeting minutes and Community Action Team Change Log.)

    - Provide DOH with Health Council meeting minutes, … to maintain a connection with the Health Council…  (See attached MCCH meeting minutes, Change logs, and system planning documents and tools.

    - Document that participation in the Community Action Team is maintained…  (See Community Action Team meeting minutes.)

    - Engage the Health Council in supporting the Community Action Teams recommendations…  (The Health Council is engaged in support as stipulated in the attached MOU.)

    - Recommend … a measurement plan… (Recommendations and their integration into the Profile and Plan are pending.)

  - Provide coordination services, …,  for the Community Health Council’s community health improvement process Community Action Cycle [Teen Pregnancy] … , starting October 1, 2003, by:

    - Coach and document … the second Community Action Team … starting by October 1, 2003.  The initial meeting of the second Community Action Team (Teen Pregnancy Committee) took place on September 11, 2003.  (See attached minutes.)

    - Assure that the … Community Action Team meets twice a month for a minimum of 4 hours total per month… (See minutes of meetings.)

    - Develop a Charter…  [1 Nov 03] In process.

    - Provide the Health Council and DOH documentation of the work of the Community Action Team… (See attached meeting minutes and Community Action Team Change Log.)

    - Provide DOH with Health Council meeting minutes, … to maintain a connection with the Health Council… (See attached MCCH meeting minutes, Change logs, and system planning documents and tools.

    - Document that participation in the Community Action Team is maintained… (See Community Action Team meeting minutes.)

    - Engage the Health Council in supporting the Community Action Teams recommendations… (The Health Council will be engaged in support as stipulated in the pending MOU.)

    - Recommend … a measurement plan… (Recommendations and their integration into the Profile and Plan are pending.)