Quay County Maternal Child and Community Health Council

2nd Quarter FY04 Scope of Work Log

January 15, 2004

Please note that several documents in this packet are two-sided.

- Hire a contractor to provide coordination services for the Comprehensive Community Health Council in the Community Health Improvement Process activities:

  - Develop, maintain, and document the Comprehensive Community Health Council’s community health improvement Process’ Community Building Cycle by:

    - Engage and maintain a Health council Coordinator who is responsible for facilitating health council activities in accordance with the scope of work…  Jason Nemrow continues under contract, as of 1 Aug 03, to serve as a co-coordinator.

    - Provide Quarterly Reports which are the Scope of Work Logs and the Community Change Logs… [15 Oct 03; 15 Jan 04; 15 Apr 04; 15 Jul 04]  This is the 15 Jan 04 report.

    - Administer the Community Health Improvement Process Self-Assessment Tool… [15 Apr 04]  This will be done in the 3rd quarter as stipulated.

    - Provide documentation of attendance at the Community Health Improvement Training Institute (CHITI) courses…  [15 Jul 04]  Documentation of attendance is included in Appendix 1.A.4, including the approved substitution of a two-day Community Systems Change training for some attendance.  The attendance in this quarter fulfills the CHITI course attendance requirement for the contract period.

    - Review and update when appropriate the Comprehensive Community Health Council organizational documents… [15 Jan 04]  Updated organizational documents are included in Appendix 1.A.5.

    - Ensure no one member in a voting or decision-making role is in both the health council and the fiscal agent organization….  The by-laws of the MCCH Council have been updated to address this issue.  The updated by-laws are included in Appendix 1.A.5.

    - Provide DOH with a current list of members, demonstrating diverse membership… [15 Jan 04]  A current list of members is included in the Member MOU, which is included in Appendix 1.A.8.  A current list of officers is included in the information flyer in Appendix 1.A.5.

    - Provide DOH with Memoranda of Understanding (MOUs) or… [15 Jan 04] The Member MOU is included in Appendix 1.A.8.

    - Provide DOH and disseminate within the community a flyer or brochure which documents… [15 Jan 04] The Council-approved Flyer is included in Appendix 1.A.5.

    - Provide DOH with documentation of participation and provision of an exhibit in one statewide meeting… [15 Jul 04] The Community Health Improvement Exposition was attended on the 8th and 9th of December 2003.

    - Provide DOH with documentation of participation in a minimum of three quarterly Public Health Division District Area Health Council Leadership meetings… [15 Jul 04] District Health Council Leadership meetings were attended

  - Update the comprehensive Community Health Council’s community health improvement process’ Assessment & Prioritization Cycle, …, by:

    - Review and update where appropriate the comprehensive Community Health Profile… [30 Mar 04] Not yet reported.

    - Review and update where appropriate the comprehensive Community Health Improvement Plan… [30 Mar 04] Not yet reported.

    - Provide to anyone or any group in the community, …and distribute to other coalitions at lease annually. Current Profile and Plan are on display at http://www.quaymcch.com and http://ihi.quix.us.  FY04 updates will be available at the http://ihi.quix.us by the 30 Mar 04.

  - Provide coordination services, …,  for the Community Health Council’s community health improvement process Community Action Cycle [Youth Illegal Substance Use] … , starting September 1, 2003, by:

    - Attendance at all 4 days …   of the new CHITI Systems Approach Classes/Coaching network meetings is required by all coordination staff… We have elected to sponsor and attend a 2-day DOH Community Systems Change Process training (documented in Appendix 1.A.4) in lieu of the first three days of the required training.  This training took place on the 28th and 29th of October 2003.

    - Coordinate the first Community Action Team … starting by September 1, 2003. The first Community Action Team (Substance Abuse Committee) met and was coordinated as specified on August 15, 2003.

    - Assure that the … Community Action Team meets twice a month for a minimum of 4 hours total per month… Minutes of meetings are included in Appendix 1.C.3.

    - Provide the Health Council and DOH documentation of the work of the Community Action Team… Minutes of meetings are included in Appendix 1.C.3. The Community Action Team Change Log is included in Appendix 1.C.4.

    - Provide DOH with Health Council meeting minutes, … to maintain a connection with the Health Council…  All minutes and products produced are distributed to Council members and the community through the http://ihi.quix.us website.  Minutes of MCCH Meetings with Committee Reports are included in Appendix 1.C.5.

    - Document that participation in the Community Action Team is maintained…  Minutes of meetings are included in Appendix 1.C.3.

    - Engage the Health Council in supporting the Community Action Teams recommendations…  The Health Council is engaged in support as stipulated in the established MOU.

    - Recommend … a measurement plan… Recommendations and their integration into the Profile and Plan are pending.

  - Provide coordination services, …,  for the Community Health Council’s community health improvement process Community Action Cycle [Teen Pregnancy] … , starting October 1, 2003, by:

    - Coach and document … the second Community Action Team … starting by October 1, 2003.  The initial meeting of the second Community Action Team (Teen Pregnancy Committee) took place on September 11, 2003.

    - Assure that the … Community Action Team meets twice a month for a minimum of 4 hours total per month… Minutes of meetings are included in Appendix 1.D.2.

    - Develop a Charter…  [1 Nov 03] The approved Charter is included in Appendix 1.D.3.

    - Provide the Health Council and DOH documentation of the work of the Community Action Team… Minutes of meetings are included in Appendix 1.D.2. The Community Action Team Change Log is included in Appendix 1.D.4

    - Provide DOH with Health Council meeting minutes, … to maintain a connection with the Health Council… All minutes and products produced are distributed to Council members and the community through the http://ihi.quix.us website.  Minutes of MCCH Meetings with Committee Reports are included in Appendix 1.C.5.  System Planning Documents are included in Appendix 1.D.5.

    - Document that participation in the Community Action Team is maintained… Minutes of meetings are included in Appendix 1.D.2.

    - Engage the Health Council in supporting the Community Action Teams recommendations… The Health Council is engaged in support as stipulated in the Charter.  The approved Charter is included in Appendix 1.D.3.

    - Recommend … a measurement plan… Recommendations and their integration into the Profile and Plan are pending.